## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | Acceptance Testing | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | GT; 10/9/2019; Completed with no issues. | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | GT; 10/9/2019; Completed with no issues. | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | GT; 10/9/2019; Completed with no issues. Spaces do not create problems | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | GT; 10/9/2019; Accepts alphanumeric, disregards the non-alphanumeric characters | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Doesn't check the first character for non alphanumeric characters
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | GT; 10/9/2019; Does not accept repeated names | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | GT; 10/9/2019; List is shown | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | GT; 10/9/2019; The number is shown, easy to locate | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | GT; 10/9/2019; Game starts | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | GT; 10/10/2019; Game starts and players are assigned. | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | GT; 10/10/2019; Error is stated, does not move off the page | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | GT; 10/10/2019; | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | GT; 10/10/2019 | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | GT; 10/10/2019 | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | GT; 10/10/2019 | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | GT; 10/9/2019; The board looks correct as it should | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Every time a player makes a move, the other player's board flips
As a player I want to make a move so that I can play checkers. | Given there is a piece I can take, then I must take that piece |  |  | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that there are no jumpable moves then I must move my piece |  |  | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I just jumped over a piece, and that I can jump again, then I must jumped again |  |  | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Player can make a normal jump instead of a multijump
| Given that I jump over a piece and capture it, then I expect the piece to be taken and removed from the game. |  |  | Pass | GT; 11/5/2019; Completed with no issues. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given that I make it to the other side, I expect my piece to become a kingpiece |  |  | Fail | The board is being updated, however, it is not being reflected in the UI. | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Nothing happens
| Given there are no more possible moves to make, end the game. |  |  | Fail | Function calls and methods are ready in the backend, has to be implemented in the UI | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Game continues, unplayable
As a player I want to make a move such that the game is still valid. | Given the game is in session when I have no more pieces then I expect to be given a loss and the opposing player a win. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given the game is in session when my opponent no more pieces then I expect to be given a win and the opposing player a loss. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given it is my turn when I can't move any of my pieces then I expect to be given a loss |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Game continues, unplayable
| Given it is my opponent's turn when they can't move any of their pieces then I expect them to be given a loss |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given I am playing a game and it is my turn, when I take a piece, then I expect that piece to no longer be shown on the board. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
As a piece I want to reach the opponenets side so that I can turn into a kingpiece. | Given the game is in session when a player makes its token reach the other side, then I expect the token to turn into a kingpiece. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Nothing happens
| Given I have a kingpiece when I choose to move it then I expect the option to move forward or backward depending on my position. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> Can't king pieces
As a Spectator, I want to view a game so that I can tantalize the players playing. | Given there is a game running when a piece is moved then I expect to be updated on from where and where to the piece was moved. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given there are two payers in a game, when I click on a player's name, then I expect to be added as a spectator |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
As a computer, I want to make correct and significant moves so that the player faces a challenge when playing the game. | Given I am playing a game against a computer, when I make a move, then I expect the computer to make a move that can be determined to be significant. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
As a player, I want to forfeit the game so that the game ends. | Given a game is in progress, when a player resigns, then show the opponent that the player has resigned and an option to exit the game. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19> The player that resigned is redirected to the home, the other player is left in the game
| Given a game has just finished, when I click exit, then I expect to be exited from the game. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>
| Given a game is in progress, when a player wins, then the opponent is granted a loss and the player is given a win. |  |  |  |  | Pass | GT - (11/21/2019) |  | Team J3M <11/12/19>